# Project Task Table (Consecutive Task Numbers)

|  |  |  |  |
| --- | --- | --- | --- |
| Task | Task Name | Time (Days) | Dependency |
| A | Project Planning | 2 | — |
| B | Requirement Gathering & Analysis | 4 | A |
| C | Feasibility Study | 2 | B |
| D | System Design (UML, Diagrams, DB) | 5 | C |
| E | Security & Compliance Review | 3 | D |
| F | Implementation (Frontend & Backend) | 10 | D |
| G | Integration & Testing | 4 | F |
| H | Stakeholder Review & Approval | 2 | E, G |
| I | Deployment | 2 | H |
| J | User Training & Documentation | 3 | I |